|  |
| --- |
| **GREENHAM COMMON 100 YEARS OF WAR AND PEACE - TIMELINE** |
| **DATE** | **TIME** | **EVENT** | **LOCATION** **(FULL ADDRESS DETAILS ON PAGES 4 & 5 BELOW)** |
| Sunday, 13th August – Friday, 18th August |  | Production build days | 101 Outdoor Arts Creation Centre |
| Saturday 19th and Sunday 20th August – tbc |  | Production build days | 101 Outdoor Arts Creation Centre |
| Monday, 21st August to Thursday 24th August inclusive | 1000-1200 | Watermill Summer Schools - Installation B: Scene 1: 1940 – Evacuees: Children aged 8 – 11 years and adult plus Encore group and adult Fourth Wall group. Plus costume fittings during these sessions to be arranged | The Watermill Theatre |
| Monday 28th August to Monday 4th September | 0900-1200 | Production build days | 101 Outdoor Arts Creation Centre |
| Tuesday 29th August – Thursday 31st August inclusive | 0900-1200 | Watermill Summer Schools -Installation A: Scene 1: 1930 – Children at school aged 10 – 12 yearsPlus costume fittings tba | 101 Outdoor Arts Creation Centre |
| Tuesday 29 August – Thursday 31st August inclusive | 1300-1600 | Watermill Summer Schools - Installation A Scene 2: 1930 – Children at school aged 12-14 yearsPlus costume fittings tba | 101 Outdoor Arts Creation Centre |
| Tuesday, 29th August to Friday 1st September inclusive |  | Production Days with Sophie and production team at 101 and NGA. Additional rehearsals may be scheduled by director Sophie and choreographer Rachel | 101 Outdoor Arts Creation Centre |
| Wednesday, 30th August | 1000-1300 | Heads of Department meeting | 101 Outdoor Arts Creation Centre |
| Wednesday, 30th August | 1400-1700 | Rachel, Sophie & Kris (& Andy Richardson from Apollo Big Band if possible) | 101 Outdoor Arts Creation Centre |
| Wednesday, 30th August | 1830-2100 | Dance Hall rehearsal (For the 1940s dancers, the Glider factory workers, Factory Peggy & Frank) | 101 Outdoor Arts Creation Centre |
| Thursday, 31st August |  | Filming USAF scene on Greenham Business Park location tbc | 101 Centre / Greenham Business Park location tbc |
| Friday 1st September | 1000-1300 | Francis Green rehearsal | 101 Outdoor Arts Creation Centre |
| Friday 1st September | 1400-1700 | Main Peggy rehearsal | 101 Outdoor Arts Creation Centre |
| Friday 1st September  | 1700-1800 | Choir – Optional Walk on Common to site with production team member | Meet at New Greenham Arts |
| Friday 1st September | 1830- 2130 | Full Sing Through Following Summer Break – All Choir | Horris Hill School Chapel |
| Friday, 1st September | 1830-2100 | Performers - Evening of 1st September – Walk on Common with Production team, Members of Cast and Choir and Performance Director | Greenham Common(Out door clothes needed) |
| Saturday, 2nd September | 10.00-1700 | Performer Rehearsals of First Half of Script Schools scenes and evacuee scenes, including the Rage Chorus, the Watermill, Main Peggy.(No dance of the Domestic Servants as not available) Watermill PerformersSaturday 2nd September - Group 2 & 3 - both school groups 10.00-13.00Group 1: Evacuee group 14.00-16.00Rage chorus from 1330  | 101 Outdoor Arts Creation Centre |
| Saturday, 2nd September | 1400-1700 | All Choir plus first half Performers for rehearsal of all first half - Rehearsals plus costume fittingGlider Factory call from 1500-18001940’s Dancers call from 1500-1800Peggy call from 1500-1800Frank call from 1500-1800 | 101 Outdoor Arts Creation Centre |
| Sunday 3rd September | 10.00-13.00 | Performer Rehearsals of Second Half of Script – plus costume fitting, Asian families attending from 1000Main Peggy required from 1000Francis Green required from 1000 | 101 Outdoor Arts Creation Centre |
| Sunday, 3rd September | 1400-19.00 | 1400 to 1900 – All Choir and All second half PerformersRehearsal1400 to 1900 – All Watermill Performers1500 -1900 ALL CAST AND CHOIR 1700 COMPLETE RUN Adults please bring picnic meal Children – we will provide a mid-afternoon meal | 101 Outdoor Arts Creation Centre |
| Sunday, 3rd September | 1500-1900 | All cast to join for run through of finale | 101 Outdoor Arts Creation Centre |
| Sunday, 3rd September | 1600-1715 | Event - Missiles, Politics and Peace talk with BBC Broadcast Recording  | Corn Exchange, Newbury |
| Monday, 4th September | 1000-1700 | All sound cue for installation and show | Greenham Trust Offices |
| Monday, 4th September | 1700-1800 | Jess Spath & Rachel Drazak (peace camp rehearsal) | On Site |
| Monday, 4th September – Sunday, 10th September |  | Production Team and Security arrive for build on central common site – until and including Sunday 10th Sept | Outdoor site on Common – in and around Central Cross – vehicle access by Control Tower |
| Monday 4th September  | Afternoon and evening | Media Training including recording at Memories event at Royal British Legion |  |
| Monday, 4th September | 1900-2030 | Event - Memories of Greenham Common  | Royal British Legion, Newbury |
| Monday, 4th September | 18.30 to21.30 | Full Choir – BBC recording | Horris Hill School Chapel |
| Monday, 4th September | 1830-2100 | 1984 Peace Camp Rehearsal (Peace camp women, police and USAF required) working Sophie & Kris | On site |
| Monday, 4th September | 1830-2100 | The dance of the domestic rehearsal (Rachel & Nocturne) | On site |
| Tuesday, 5th September | 1000-1700 | Sophie & Joe to run through all video cues | TBC |
| Tuesday, 5th September | 1900-2015 | Event - The Characters on the Common – panel chat show with BBC Broadcast Recording | Corn Exchange, Newbury |
| Tuesday, 5th September | 18.30-21.30 | Choir rehearsal with possible rehearsal for installation scenes | Horris Hill School Chapel |
| Tuesday, 5th September | 1830-2100 | The Glider factory actors with Rachel and Sophie rehearsal | On stage, on site |
| Tuesday, 5th September | 1830-2100 | Peace camp women and artists to create the camp with Kris | On site |
| Tuesday, 6th September |  | Social media training | Venue tbc |
| Wednesday, 6th September | 1400-1530 | Event - Exploring the History of the Common | Shaw House |
| Wednesday, 6th September | 1400-1700 | Main Peggy, Francis Green, Factory Peggy & Frank rehearsal on main stage, including sound check.Maggie, Andy Kemp & Adam Taylor also required from 1700 to 1800 | On stage, on site |
| Wednesday, 6th September | 1800-2200 | Technical Rehearsal – All speaking performers, available choir members and some Apollo Big Band members | Greenham Common  |
| Thursday, 7th September | 1400-1700 | 1940s dance hall rehearsal installation and finale (with Sophie & Rachel) Factory Peggy, Eisenhower, Frank, 1940’S dancers & Apollo Big band required | On site |
| Thursday, 7th September | 1600-1700 | Children’s choir rehearsal | Horris Hill School Chapel |
| Thursday, 7th September | 1800-2200 | Dress rehearsal ALL. Costume open from 4pm – all cast to arrive by 4.45pm at New Greenham Arts for changing. Unless other arrangements made1800-2000 All Installations2000-2200 Finale | Greenham Common |
| Friday, 8th September | 1130-1300 | Event - Mike Relph’s walk / tour of the Common | Greenham Common |
| Friday, 8th September | 1100-1400 | Event - Decontamination Suite Tours Small school and group tours by arrangement  | Greenham Common |
| Friday, 8th September | Time tbc | Event – Greenham Trust book launch tbc | West Berkshire Museum |
| Friday, 8th September | 1800-1930 | Event - Ticketed Decontamination Suite Tours  | Greenham Common |
| Friday, 8th September | Costume from 1600 to 1730 for cast.1830-21.30 | Event - Main Greenham: 100 Years of War and Peace event **Theatrical installations, Procession and Finale Show – Food and Re-enactors****ALL** | Greenham Common |
| Saturday, 9th September | 1130-1300 | Event - Mike Ralph’s walk / tour of the Common | Greenham Common |
| Saturday, 9th September | 1100-1400 | Event - Ticketed tours - Decontamination Suite Tours | Greenham Common |
| Saturday, 9th September | 1445-1600 | Event - How we Made the Show - With Free Tea and Cake and Songs from the show with InCantata Choir  | Greenham St Mary’s Church Hall |
| Saturday, 9th September | 1800-1930 | Event - Ticketed tours - Decontamination Suite Tours | Greenham Common |
| Saturday, 9th September | Costume from 1600 to 1730 for cast.1830-2130 | Main Greenham: 100 Years of War and Peace **Theatrical installations, Procession and Finale Show – Food and Re-enactors****ALL** | Greenham Common |
| Sunday, 10th September | 1530-1730 | Party – ALL  | New Greenham Arts |
| Wednesday, 4th October | 1900-2000 | Greenham: 100 Years of War and Peace – talk with Beth Flintoff | West Berkshire Museum |
| Friday, 6th October | 1900-2000 | Plants and Wildlife on Greenham Common – Talk speaker tbc | West Berkshire Museum |
| Friday, 13th October | 1900-2000 | Flight from Uganda: Talk with Pragna Hay | West Berkshire Museum |
| Friday, 20th October | 1900-2000 | Living with the Americans: Talk with Claire Burdett | West Berkshire Museum |

**Addresses:**

Greenham Common, nr Greenham Business Park, Liberty House, First St, Greenham, Thatcham, RG19 6HW

New Greenham Arts, Greenham Business Park, 113 Lindenmuth Way, Newbury, RG19 6HN

St Mary’s Greenham Church Hall, Greenham Vicarage, New Rd, Greenham, Thatcham RG19 8RZ

101 Outdoor Arts Creation Centre, Unit 101, Greenham Business Park, Communications Rd, RG19 6HN

BBC Radio Berkshire, Caversham Park, Peppard Rd, Reading, RG4 8TZ

The Watermill Theatre, Sackler Studio, Bagnor, Newbury, Berkshire, RG20 8AE

Greenham Business Park, Newbury, RG19 6HW

Shaw House, Church Rd, Newbury, RG14 2DR

West Berkshire Museum, 4 Toomers Wharf, Newbury, RG14 1DY

St Nicolas Church, W Mills, Newbury, RG14 5HG

Corn Exchange, Newbury, Market Pl, Newbury RG14 5BD

Newbury Royal British Legion, Haig House, Pelican Ln, Newbury RG14 1NP

Horris Hill School, Horris Hill, Newtown, Newbury RG20 9DJ